## Launch readiness
Launch readiness checklist
Set Status for each area using the drop-down; add an owner and evidence. Yellow cells are for you to fill in. Row 6 is an illustrative example.
| Product / offer: |  | Target date:
# | Readiness area | What "ready" means | Owner | Status | Evidence / link | Notes
1 | Proposition and target audience agreed | Value, segment and need are clear and signed off | Product lead | In progress | Example: test plan link | Illustrative example, overwrite
2 | Product content, terms and eligibility approved | Descriptions, restrictions and eligibility rules are complete and approved |  | Not started
3 | Pricing and inventory rules validated | Price and availability checks work and are approved |  | Not started
4 | Purchase and confirmation journey tested | End-to-end purchase, confirmation and change flows tested |  | Not started
5 | Property or service fulfillment validated | The delivering team can fulfil the commitment in real scenarios |  | Not started
6 | Exceptions, refunds and support processes documented | Likely failures have a recovery path and support teams can resolve them |  | Not started
7 | Communications and training ready | Customer messages and team training are in place |  | Not started
8 | Analytics and guardrails instrumented | Exposure, purchase, fulfillment and guardrail metrics can be measured |  | Not started
9 | Pilot and scale criteria agreed | Scale / iterate / pause thresholds are agreed in advance |  | Not started
Summary
| Not started | 8
| In progress | 1
| Ready | 0
| Blocked | 0
| Not applicable | 0
| Readiness % | 0%
| Go / no-go signal | Not yet ready